## Sheet1
Conestoga College
Team: | Alex Caron, Michal Drahorat, Brody Gartner, Jake Kenny
Agile Product Feature List - Backlog Template
# | Description | PD est. | By | Note: PD = Person day = 4 hours; start feature # from 101 (reserve 1-100 for other requirements)
| High Priority |  |  | Note: Only high priority items are prioritized, assigned to iteration, and estimated
Iteration 1
101 | Add Game | 1 | JK
102 | Update Game | 0.5 | JK
103 | Delete Game | 0.5 | JK
104 | Add Event | 1 | MD
105 | Update Event | 0.5 | MD
106 | Delete Event | 0.5 | MD
107 | Produce Reports | 1 | JK
Iteration 2
108 | Game Library | 2 | JK, MD
109 | Employee Features | 1 | JK
110 | Login event | 2 | JK
111 | Logout event | 1 | JK
112 | Search Bar | 1 | MD
113 | Add Item to Wishlist | 1 | JK
Iteration 3
114 | Add Credit Card | 1 | JK,MD
115 | Update Credit Card | 1 | MD, JK
116 | Delete Credit Card | 1 | JK, MD
117 | Add to cart | 2 | JK
118 | Remove from Cart | 1 | JK
119 | View Cart | 0.5 | MD
120 | Add to Library | 1 | JK
Transition
121 | Compiling Binder | 4
122 | Product ID guide | 1
123 | Project Deployment guide | 3
| Medium Priority |  |  | Note: Medium and Low are prioritized but not yet assigned to iteration, nor estimated
Low Priority