## Sheet1
Conestoga College
Team: | Alex Caron, Michal Drahorat, Brody Gartner, Jake Kenny
Release Plan Summary
|  | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: Sept-22 | Due: Oct-13 | Due: Nov-3 | Due: Dec-22 | Due: Jan-5
# | Feature / Requirement
1 | Project Charter | 4
Team Charter
Project Plan
101 | Add Game |  | 1
102 | Update Game |  | 0.5
103 | Delete Game |  | 0.5
104 | Add Event |  | 1
105 | Update Event |  | 0.5
106 | Delete Event |  | 0.5
107 | Produce Reports |  | 1
108 | Game Library |  |  | 3
109 | Employee Features |  |  | 1
110 | Login event |  |  | 2
111 | Logout event |  |  | 1
112 | Search Bar |  |  | 1
113 | Add Item to Wishlist |  |  | 1
114 | Add Credit Card |  |  |  | 1
115 | Update Credit Card |  |  |  | 1
116 | Delete Credit Card |  |  |  | 1
117 | Add to Cart |  |  |  | 2
118 | Remove from Cart |  |  |  | 1
119 | View Cart |  |  |  | 0.5
120 | Add to Library |  |  |  | 1
121 | Compiling Binder |  |  |  |  | 4
122 | Product ID sheet |  |  |  |  | 1
123 | Project Deployment Guide |  |  |  |  | 3
| Work Effort in Person Days (PD) | 4 | 5 | 9 | 7.5 | 8 | 33.5 | Target: 135 to 150 PD for team of 3
Given: 1 PD = 4 hours
Estimate: 3 PD per week = 45 PD per member; 135 PD for team of 3